## Consultation Gantt Chart
| Confirmed | Maybe
reg 14
reg 16
|  | March |  |  |  | April |  |  |  |  | May |  |  |  | June |  |  |  | July
District | Plan | 4th | 11th | 18th | 28th | 1st | 8th | 15th | 22nd | 29th | 6th | 13th | 20th | 27th | 3rd | 10th | 17th | 24th | 1st | 8th | 15th | 22nd | 29th
Babergh | Long Melford
Babergh | Aldham | bar: March 4th to April 8th
Mid Suffolk | Woolpit | bar: March 4th to April 15th
Mid Suffolk | Eye
Babergh | Fressingfield | bar: April 1st to May 13th
Babergh | Little Waldringham
Babergh | Capel St Mary
East Suffolk | Beccles | bar: May 6th to July 29th
West Suffolk | Newmarket
Mid Suffolk | Needham Market
East Suffolk | Mutford | bar: April 22nd to June 3rd
East Suffolk | Reydon | bar: April 22nd to June 3rd
East Suffolk | Southwold | bar: May 6th to July 29th

## Progress
Qualifing Body | Designating the neighbourhood area (reg.7*) and, if appropriate, the neighbourhood forum (reg. 10*) | Preparing a draft neighbourhood plan | Pre-submission publicity and consultation (reg.14*) | Submission of a neighbourhood plan to the local planning authority (reg 15*) and publication of plan proposal by the LPA (reg. 16*) | Independent examination (reg. 17 and 18*) | Referendum (reg. 19 and 20*) | additional information | *Town and country Planning, England, The Neighbourhood Planning (General) Regulations 2012
East Suffolk
Aldringham cum Thorpe | 2016-05-01
Barnby | 2018-06-01
Beccles (reviewed - Beccles parish only) | [5 empty] | yes vote, made Sept 21 | examination summer 2021
Bredfield | [5 empty] | yes vote - made May 2021 | Additional Post-Reg16 consultation June 2020. Examination sept 2020.
Bungay |  |  | 2021-11-01 | deadline: June 6th |  | made Nov 2022 | ref to be held nov 22
Campsea Ashe | 2023-01-01
Carlton Colville |  | draft seen Aug 21 | DEADLINE: May 22 | inf R16 seen Jan 23 |  |  | removal of AECOM design code following R14 coments, saw inf R16 jan 23
Corton | 2020-03-01
Earl Soham | 2017-12-01
Easton | 2017-12-01 |  | DEADLINE: 20 MARCH 23
Framlingham | [5 empty] | yes-vote/made 2017. | Review: discussions start March 2021.
Great Bealings | [5 empty] | yes-vote/made 2017.
Halesworth |  | inf: sept 21 | 2021-12-01 | 2022-08-03 |  | ref : 02/02/23
Henstead with Hulver St | 2016-09-01
Kelsale cum Carlton | 2017-11-01
Kesgrave | [5 empty] | yes vote - made May 2021
Kessingland | [5 empty] | yes-vote/made 2017 | includes allocations
Leiston | [5 empty] | yes-vote/made 2017
Lound with Ashby, Herringfleet and Somerleyton |  |  | 2021-02-01 | 2021-10-13 |  | adopted July 2022
Lowestoft |  | inf: july 22 | DEADLINE: 9 MARCH 23
Martlesham | [5 empty] | yes-vote/made 2018
Melton | [5 empty] | yes-vote/made 2018
Mettingham, Barsham, Shipmeadow, Ringsfield & Weston | 2020-03-01
Mutford | [5 empty] | Yes vote, made 2019
Otley | 2019-04-01
Oulton |  |  | 2021-11-01 | 2022-06-24 |  | ref 20/02/23
Oulton Broad (superceded) | 2020-03-01 | [5 empty] | In december 2018 the original neighbourhood plan area was superceded with a revised area
Playford | 2017-06-01
Rendlesham | [5 empty] | yes-vote/made 2015 | includes allocations
Reydon | [5 empty] | yes vote, made May 2021 | examination summer 2020
Rushmere St Andrew |  |  | 2021-11-01 | deadline: june 6th | POST EXAM MODS
Saxmundham |  |  | 2021-12-01 | 2022-09-02 | public hearing: 27/02/23
Shadingfield, Sotterley, Willingham and Ellough |  |  | 2022-03-01 | 2022-09-07 | 2022-11-01
Southwold | [5 empty] | adopted feb 2022 | Amendments to Housing Policies Jan'21
Trimley St Mary | 2017-02-01
Ufford | 2022-04-01
Walberswick
Westerfield | 2021-09-01
Wenhaston with Mellis Hamlet | [5 empty] | yes-vote/made july 2018
Wickham Market |  |  | 2019-04-01 | 2022-12-01
Woodbridge | 2015-05-01 | [5 empty] | Work ceased on plan in Dec 2016
Worlingham |  |  | 2021-06-01 | 2022-02-01 |  | made nov 2022 | ref Nov 22
Mid Suffolk
(Diss, Raydon, Burston & Shimpling, Scole = South Norfolk; Palgrave, Stuston, Brome & Oakley = Mid Suffolk)
Ashbocking | 2019-11-01
Bacton | 2022-07-21
Badwell Ash & Long Thurlow | 2022-09-01
Battisford | 2019-12-01
Beyton |  |  | 2021-04-01 | exp: March?
Botesdale and Rickinghall | [5 empty] | Yes vote, made - Jan 2020
Debenham | [5 empty] | Yes vote, made march 2019 | Contains allocations
Diss and District |  |  | V2: APRIL 22 ...01/08/2021 | 2022-12-01 |  |  | 2nd r14 in april 2022.
Drinkstone | [5 empty] | Yes Vote (May 2021), adopted.
Elmswell |  | inf march 21 | 1st July 22 |  |  |  | inf early 2021.
Fressingfield | [5 empty] | yes vote, made March 2020
Eye | [5 empty] | Yes Vote (May 2021), adopted.
Groton | 2022-07-01
Haughley |  | seeking info for review, Oct 22 |  |  |  | Yes vote, made 2019
Hoxne |  | INF: Aug/sept 2021 | 2022-02-01 | EXP Feb???
Laxfield | [5 empty] | yes vote march 2022
Mendlesham |  |  | REVIEW march 21 | REVIEW 01/09/2021 |  | yes-vote/made 2017. REVIEW: Adopted Nov 2022. | Modification: Review R14 stage March'21, R16 August '21.
Needham Market | [5 empty] | yes-vote/made march 2022 | Rethinking NP with a large urban extension
Old Newton & Dagworth with Gipping | 2020-02-01
Redgrave |  |  |  | 2021-07-01 |  | yes vote, made July 22 | ref upcoming - may not pass????
Stowupland | [5 empty] | yes vote/made 2019
Stradbroke | [5 empty] | yes-vote/made 2019 | Contains allocations
Thorndon | [5 empty] | yes vote/made March 2022 | post-exam mods to LGS
Thurston | [5 empty] | Yes vote/made 2019
Walsham Le Willows | 2018-07-01 |  | 2022-12-01 | EXP: after may elec
Wetheringsett (com Brockford) | 2021-01-01 |  | 2022-08-01 | DEADLINE 10 march 23
Wilby | [5 empty] | Yes Vote (May 2021), adopted.
Woolpit |  |  |  |  | mods post examination | yes vote, made Oct 22 | Additional 2week consulation june/july 2020
Babergh
Acton | 2021-10-01 |  | EXP early april
Aldham | [5 empty] | yes vote/made jan 2020
Assington |  |  |  |  | 2021-07-01 | yes vote/ made march 22
Bentley |  |  |  | 2021-08-27 | 2022-08-01 | yes
Boxford |  | inf: spring '21 | 2021-09-01 | DEADLINE: april 22 |  | yes vote, made oct 2022
Brettenham | 2021-01-01
Bures & Bures St Mary (with Braintree DC) | oct 2021
Capel St Mary |  |  | V2 r14 exp winter '21
Chelmondiston(and Pin Mill ) | [5 empty] | yes vote/ made march 22
Chilton | 2017-12-01
Copdock and Washbrook | [5 empty] | NO VOTE - March 2022. | feb '23 : re-writing, removal of allocations
East Bergholt |  | preparing review/mods |  |  |  | yes-vote/made 2016 | REVIEW - 2021
Edwardstone | 2021-03-01 |  | EXP: Ater may elec
Elmsett | [5 empty] | Yes vote, made 2019
Glemsford | 2017-10-01 | EXP
Great Walding Field | 2017-07-01 |  | 2022-08-01
Hadleigh | 2015-06-01 | [5 empty] | Working group was disbanded july 2017. may make a re-appearance??
Hartest |  |  | 2021-03-01 |  |  |  | Reg14 (V3) jan 2021
Hitcham | 2020-01-01 |  | after may elect - summer
Holbrook |  |  | 2021-12-01 | 2023-01-01
Lavenham |  | REVIEW: inf view 5th Oct | 2023-02-01 |  |  | yes-vote/made 2016 | review process: Autumn 2022
Lawshall |  |  | R14 review: Nov 22 |  |  | yes-vote/made 2017 | review procress begin Oct 22.
Little Cornard |  |  | 2021-05-01 | 2021-12-01 |  | yes vote/ made July 22
Little Waldingfield | [5 empty] | yes vote/ made march 22
Leavenheath |  | 2021-03-01 | 2021-10-01 | 2022-10-01
Long Melford |  |  |  | 2021-11-01 |  | yes vote/ made Oct 22
Newton | [5 empty] | yes vote/ made march 22
Sproughton | 2020-04-01 |  | 2021-11-01 | 2023-02-01
Stoke by Nayland | 2017-12-01
Stutton | 2018-10-01 |  | 2021-12-01 | 2022-10-01 | 2022-11-01 |  | parish council website inactive/no longer exists (aug 21). Call for sites summer 21.
Tattingstone | 2021-07-01 | [5 empty] | des'd July '21
Whatfield | [5 empty] | yes vote/ made march 22
Wherstead | 2020-09-01 |  | 2021-11-01 | 2023-01-01
Woolverstone | 2018-10-01
West Suffolk
Barrow cum Denham | 2019-06-01
Barton Mills | 2022-03-01
Barningham | 2017-04-01
Exning | 2018-06-01 | [5 empty] | des'd - overlap with newmarket 2018.
Freckenham | 2018-11-01 |  | EXP. R14 2021
Great Barton | 2019-01-01 |  |  |  |  | Yes Vote, made June 2021
Hargrave | 2015-11-01 |  |  |  |  | yes vote, made july 2018 | Review exp- summer '21
Horringer cum Ickworth | 2022-03-01
Ixworth and Ixworth Thorpe | 2017-07-01 |  | EXP nov 21
Lakenheath | 2021-02-01
Mildenhall | 2023-02-01
Newmarket | 2018-06-01 |  |  |  |  | yes vote, made july 2020 | Newmarket repeated reg 14 consultation
West Row | 2021-05-01
Wickhambrook | 2021-10-01 | [5 empty] | issues re hedge removal at chucrh.
Withersfield | 2020-01-01 |  | 2022-12-01
Worlington | 2021-08-01
Note on D55: Georgia Teague: additional R14 expected 2022